## UI
| Project Name: | NORTH-STAR
| Client: | ABS-CBN International
| From: | Benjamin Abraham
| To: | Akshay Indraganti
| Knowledge Transfer: | FrontEnd Development
Sr.No | Action Items | Description | Date | KT Status | Reverse KT | Reverse KT Date | Comments | Owner
1 | Nort-Start Overview | Overview | 2022-07-01 | Completed | Completed | 2022-07-06 |  | Benjamin
2 | About Storybook | What is Storybook | 2022-07-01 | Completed | Completed | 2022-07-06 |  | Benjamin
3 | About Atomic Design System | What is our design system and folder structure | 2022-07-01 | Completed | Completed | 2022-07-06 |  | Benjamin
4 | Creation of Element. | How to create an Element | 2022-07-01 | Completed | Completed | 2022-07-07 |  | Benjamin
5 | Using Element in Component | How to use Element in aComponent | 2022-07-01 | Completed | Completed | 2022-07-07 |  | Benjamin
6 | About IMP-Design-System | How IMP-design-system is a library | 2022-07-01 | Completed | Completed | 2022-07-07 |  | Benjamin
7 | About News-web repository | How does news-web repository works | 2022-07-01 | Completed | Completed | 2022-07-07 |  | Benjamin
8 | Walkthrough of PUSH website | Detailed walkthrough of PUSH website | 2022-07-05 | Completed | Completed | 2022-07-06 |  | Benjamin
9 | Figma explanation | Walkthrough of figma. | 2022-07-05 | Completed | Completed | 2022-07-06 |  | Benjamin
| Item | Access and Permissions
| Email | Domain Creation - Ticket Raised
VPN
Azure DevOps
JIRA
Confluence

## Superdesk
| Project Name: | NORTH-STAR
| Client: | ABS-CBN International
| From: | Pavan Kumar
| To: | Akshay
| Knowledge Transfer: | Functional Testing
Sr.No | Action Items | Description | Date | KT Status | Reverse KT | Reverse KT Date | Comments | Owner
1 | North-Star Overview | Overview | 2022-07-04 | Completed | Completed |  |  | Pavan
2 | Creation of Pusk desk templates | Push Desk -Article | 2022-07-05 | Completed | Completed |  |  | Pavan
3 | Creation of Pusk desk templates | Push Desk -Photo album-Video Article | 2022-07-05 | Completed | Completed |  |  | Pavan
4 | SMTP-Email config | Email Templates for Push Desk | 2022-07-06 |  |  |  |  | Pavan
5 | Defects-Understanding | Open Issues and User management Discussion | 2022-07-07 |  |  |  |  | Pavan
| Item | Access and Permissions
Email
VPN
Azure DevOps
Amplitude/Analytics
JIRA
Confluence

## Scrum
| Project Name: | NORTH-STAR
| Client: | ABS-CBN International
| From: | Satish Kubal
| To: | Akshay
| Knowledge Transfer: | Scrum
Sr.No | Action Items | Description | Date | KT Status
1 | Scrum Meetings | Daily Standup | 2022-07-04 | Completed
2 |  | Sprint Review | 2022-07-04 | Completed
3 |  | Sprint Retrospective | 2022-07-04 | Completed
4 |  | Sprint Planning | 2022-07-04 | Completed
5 |  | Internal Connect with IMP team | 2022-07-04 | Completed
6 | Timesheet | Fill weekly timesheet and submission | 2022-07-04 | Completed